## Sheet1
|  | Sept | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June
| Week Starting … | 30 - Sept | 7- Oct | 14 - Oct | 21 - Oct | 28 - Oct | 4 - Nov | 11 - Nov | 18 - Nov | 25 - Nov | 2 - Dec | 9 - Dec | 16 - Dec | 23 - Dec | 30 - Dec | 6 - Jan | 13 - Jan | 20 - Jan | 27 - Jan | 3 - Feb | 10 - Feb | 17 - Feb | 24 - Feb | 3 - Mar | 10 - Mar | 17 - Mar | 24 - Mar | 31 - Mar | 7 - Apr | 14 - Apr | 21 - Apr | 28 - Apr | 5 - May | 12 - May | 19 - May | 26 - May | 2 - June
1. Assignments | [37 empty] | Key
1.1. Project Proposal | [37 empty] | Holiday
1.2. Risk Assessment | [37 empty] | Reading week
1.3. Interim Report
1.4. Final Report
1.5. Poster Presentation
1.6. Progress Report
2. Sensors (LiDAR, RADAR, Camera, IR)
2.1. Research - Sensors
2.2. Set up the sensors
2.3. Collect raw data
2.4. Interpret the data
2.5. Validate sensor data
2.6. Preprocessing (Calibration, error correction)
3. Sensor Fusion
3.1. Research - Algorithm
3.2. Data Sychronisation
3.3. Perform joint sensor measurements
3.4. Offline fusion
3.5. Online fusion
4. Sensor Perception
4.1. Research - Algorithm
4.2. Program object detection algorithm
4.3. Test and validate object detection algorithm
4.4. Program object classification algorithm
4.5. Test and validate object classification algorithm
4.6. Program SLAM algorithm
4.7. Test and validate SLAM algorithm
4.8. Program path planning algorithm
4.9. Test and validate path planning algorithm
4.10. Program tracking algorithm
4.11. Test and validate tracking algorithm
4.12. Set up RC car/ robot
4.13. RC car/ robot control
4.14. Test and validate overall system
5. Other sensors (etc. Ultrasonic, Seismic)
5.1. Set up the sensors
5.2. Collect raw data
5.3. Interpret the data
5.4. Validate sensor data
5.5 Preprocessing (Calibration, error correction)